## Sheet1
Modules | Assigned Members | Planned Start Date | Actual Start Date | Planned End Date | Actual End Date | Status(frontend) | Status(backend)
Home | Gopinathan | 2023-08-01 | 2023-08-01 | 2023-08-03 | 2023-08-03 | completed | Yet to Start
Login/Regestration | Prasanna kumar | 2023-08-01 | 2023-08-01 | 2023-08-02 | 2023-08-02 | completed | In Progress
Dashboard | Jeevanandam | 2023-08-01 | 2023-08-01 | 2023-08-02 | 2023-08-02 | completed | Yet to Start
Create Action | Jeevanandam | 2023-08-02 | 2023-08-02 | 2023-08-03 | 2023-08-03 | completed | Yet to Start
My Auction/Auction Details | Prasanna kumar | 2023-08-02 | 2023-08-02 | 2023-08-03 | 2023-08-03 | completed | Yet to Start
Join Auction | Gopinathan | 2023-08-03 | 2023-08-03 | 2023-08-03 | 2023-08-03 | completed | Yet to Start
Team List/Add Team | Jeevanandam | 2023-08-04 | 2023-08-04 | 2023-08-07 | 2023-08-07 | In Progress | Yet to Start
Player List/Add Player | Gopinathan | 2023-08-04 | 2023-08-04 | 2023-08-07 | 2023-08-07 | In Progress | Yet to Start
Auction Panel | Gopinathan | 2023-08-07 |  | 2023-08-09 |  | To do | To do
Auction Panel/Summary | Jeevanandam | 2023-08-07 |  | 2023-08-09 |  | To do | To do
Auction Panel/Players | Jeevanandam | 2023-08-07 |  | 2023-08-09 |  | To do | To do
Auction Panel/Management | Prasanna kumar | 2023-08-07 |  | 2023-08-09 |  | To do | To do